## Runbook Template
Planned
[6 empty] | UK |  |  | MAL |  | IST |  | PT
Task ID | Task Description | Parallel Tasks | Responsible | Status | Date (UK) | Start time | Duration | End time | Start time | End time | Start time | End time | Start time | End time | Comments/Notes
Pre-migration Tasks
1 | Access Confluence Backend and Confluence Database |  | AVST | Not started |  |  | 0:05 |  | 8:00 | 8:00 | 4:30 | 4:30 | -0.33333 | -0.33333
2 | Install/Update CCMA |  | AVST | Not started |  |  | 0:10 |  | 8:00 | 8:00 | 4:30 | 4:30 | -0.33333 | -0.33333
3 | Turn off anonymous access in Global Permissions |  | AVST | Not started |  |  | 0:10 |  | 8:00 | 8:00 | 4:30 | 4:30 | -0.33333 | -0.33333
4 | Disable Outgoing Mail |  | AVST | Not started |  |  | 0:10 |  | 8:00 | 8:00 | 4:30 | 4:30 | -0.33333 | -0.33333
5 | On target instance, turn off email and push notifications. |  | AVST | Not started |  |  | 0:10 |  | 8:00 | 8:00 | 4:30 | 4:30 | -0.33333 | -0.33333
6 | Assess apps, mark wanted apps as needed in cloud. |  | AVST | Not started |  |  | 0:30 |  | 8:00 | 8:00 | 4:30 | 4:30 | -0.33333 | -0.33333
7 | Prepare apps. |  | AVST | Not started |  |  | 0:15 |  | 8:00 | 8:00 | 4:30 | 4:30 | -0.33333 | -0.33333
8 | Install needed apps on target instance. |  | AVST | Not started |  |  | 1:00 |  | 8:00 | 8:00 | 4:30 | 4:30 | -0.33333 | -0.33333
9 | Uninstall unwanted apps. |  | AVST | Not started |  |  | 1:00 |  | 8:00 | 8:00 | 4:30 | 4:30 | -0.33333 | -0.33333
10 | Check for duplicate users and fix any found |  | AVST | Not started |  |  | 0:15 |  | 8:00 | 8:00 | 4:30 | 4:30 | -0.33333 | -0.33333
11 | Check and fix users without an email. |  | AVST | Not started |  |  | 0:15 |  | 8:00 | 8:00 | 4:30 | 4:30 | -0.33333 | -0.33333
12 | Verify domains |  | AVST | Not started |  |  | 0:10 |  | 8:00 | 8:00 | 4:30 | 4:30 | -0.33333 | -0.33333
13 | Pre-load Attachments |  | AVST | Not started |  |  | 0:30 |  | 8:00 | 8:00 | 4:30 | 4:30 | -0.33333 | -0.33333
14 | Remove/Review space permissions |  | AVST | Not started |  |  | 0:15 |  | 8:00 | 8:00 | 4:30 | 4:30 | -0.33333 | -0.33333
15 | Confluence Migration Setup |  | AVST | Not started |  |  | 20:00 |  | 8:00 | 8:00 | 4:30 | 4:30 | -0.33333 | -0.33333
Pre-migration Tasks - Total time | [6 empty] | 24:55
Migration Tasks
1 | Execute Confluence Migration Plan |  |  | Not started |  |  | 5:30 | 5:30 | 8:00 | 13:30 | 4:30 | 10:00 | -0.33333 | -0.10417
Migration Tasks - Total time
Post Migration Tasks
1 | App migration: Scriptrunner |  | AVST | Not started |  |  | 0:05 | 0:05 | 8:00 | 8:05 | 4:30 | 4:35 | -0.33333 | -0.32986
Post Migration Tasks - Total Time | [6 empty] | 0:05
Integration Tasks
1 | Bitbucket |  | AVST | Not started
2 | Jira |  | AVST | Not started
Integration Tasks - Total Time
Global Configuration Tasks
1 | Mail Handlers |  |  | Not started
2 | Webhooks |  |  | Not started
3 | On target instance, renable push and email notifications.
4 | Global Permissions |  | AVST | Not started
5 | Grant Product Access |  | AVST | Not started
Global Configuration Tasks - Total Time
Testing Tasks
1 | Smoke tests |  |  | Not Started
2
3
4
5
6
7
8
9
10

## Data Constants
Status | IST | 4:30 | Responsible
Not started | PT | 8:00 | AVST
Delayed | MAL | 8:00 | Adenza
In Progress |  |  | AVST/Adenza
Done

## Version Info
Version 1.0.0
Last updated: Oct, 27 2025
Users may open in Excel, Google Sheets, LibreOffice, etc.